## Targets
Simple Project Management tool for chipping
Vikram, Start date 2020 Aug 07

Today	08/08/20

Date	Duration (days)	Milestones
01/08/10	30	Exploration and IP definition
31/08/10	30	Prototype implementation
30/09/10	30	Full verification
30/10/10	20	Improvements
19/11/10	5	Demo

## PlanAndStatus
	days
Available time	468
Required time	447
Slack	21

Task	Planned	Completed	Remaining
BLAST algorithm software model	125	10	115
BLAST algorithm RTL	115	10	105
Verification	150	15	135
FPGA prototyping	55	5	50
Demo	32	0	32
Signoff	10	0	10

Total	487	40	447

## TimeAvailable
Date	Day of Week	Business Day	Is Future	Vacation/Holiday	Available
01/08/20	Saturday	0	0		FALSE
02/08/20	Sunday	0	0		FALSE
03/08/20	Monday	1	0		FALSE
04/08/20	Tuesday	1	0		FALSE
05/08/20	Wednesday	1	0		FALSE
06/08/20	Thursday	1	0		FALSE
07/08/20	Friday	1	0		FALSE
08/08/20	Saturday	0	0		FALSE
09/08/20	Sunday	0	1		FALSE
10/08/20	Monday	1	1		TRUE
11/08/20	Tuesday	1	1		TRUE
12/08/20	Wednesday	1	1		TRUE
13/08/20	Thursday	1	1	1	FALSE
14/08/20	Friday	1	1	1	FALSE
15/08/20	Saturday	0	1	1	FALSE
16/08/20	Sunday	0	1	1	FALSE
17/08/20	Monday	1	1		TRUE
18/08/20	Tuesday	1	1		TRUE
19/08/20	Wednesday	1	1		TRUE
20/08/20	Thursday	1	1		TRUE
21/08/20	Friday	1	1		TRUE
22/08/20	Saturday	0	1		FALSE
23/08/20	Sunday	0	1		FALSE
24/08/20	Monday	1	1		TRUE
25/08/20	Tuesday	1	1		TRUE
26/08/20	Wednesday	1	1		TRUE
27/08/20	Thursday	1	1		TRUE
28/08/20	Friday	1	1		TRUE
29/08/20	Saturday	0	1		FALSE
30/08/20	Sunday	0	1		FALSE
31/08/20	Monday	1	1		TRUE
01/09/20	Tuesday	1	1		TRUE
02/09/20	Wednesday	1	1		TRUE
03/09/20	Thursday	1	1		TRUE
04/09/20	Friday	1	1		TRUE
05/09/20	Saturday	0	1		FALSE
06/09/20	Sunday	0	1		FALSE
07/09/20	Monday	1	1		TRUE
08/09/20	Tuesday	1	1		TRUE
09/09/20	Wednesday	1	1		TRUE
10/09/20	Thursday	1	1		TRUE
11/09/20	Friday	1	1		TRUE
12/09/20	Saturday	0	1		FALSE
13/09/20	Sunday	0	1		FALSE
14/09/20	Monday	1	1		TRUE
15/09/20	Tuesday	1	1		TRUE
16/09/20	Wednesday	1	1		TRUE
17/09/20	Thursday	1	1		TRUE
18/09/20	Friday	1	1		TRUE
19/09/20	Saturday	0	1		FALSE
20/09/20	Sunday	0	1		FALSE
21/09/20	Monday	1	1		TRUE
22/09/20	Tuesday	1	1		TRUE
23/09/20	Wednesday	1	1		TRUE
24/09/20	Thursday	1	1		TRUE
25/09/20	Friday	1	1		TRUE
26/09/20	Saturday	0	1		FALSE
27/09/20	Sunday	0	1		FALSE
28/09/20	Monday	1	1		TRUE
29/09/20	Tuesday	1	1		TRUE
30/09/20	Wednesday	1	1		TRUE
01/10/20	Thursday	1	1		TRUE
02/10/20	Friday	1	1		TRUE
03/10/20	Saturday	0	1		FALSE
04/10/20	Sunday	0	1		FALSE
05/10/20	Monday	1	1		TRUE
06/10/20	Tuesday	1	1		TRUE
07/10/20	Wednesday	1	1		TRUE
08/10/20	Thursday	1	1		TRUE
09/10/20	Friday	1	1		TRUE
10/10/20	Saturday	0	1		FALSE
11/10/20	Sunday	0	1		FALSE
12/10/20	Monday	1	1		TRUE
13/10/20	Tuesday	1	1		TRUE
14/10/20	Wednesday	1	1		TRUE
15/10/20	Thursday	1	1		TRUE
16/10/20	Friday	1	1		TRUE
17/10/20	Saturday	0	1		FALSE
18/10/20	Sunday	0	1		FALSE
19/10/20	Monday	1	1		TRUE
20/10/20	Tuesday	1	1		TRUE
21/10/20	Wednesday	1	1		TRUE
22/10/20	Thursday	1	1		TRUE
23/10/20	Friday	1	1		TRUE
24/10/20	Saturday	0	1		FALSE
25/10/20	Sunday	0	1		FALSE
26/10/20	Monday	1	1		TRUE
27/10/20	Tuesday	1	1		TRUE
28/10/20	Wednesday	1	1		TRUE
29/10/20	Thursday	1	1		TRUE
30/10/20	Friday	1	1		TRUE
31/10/20	Saturday	0	1		FALSE
01/11/20	Sunday	0	1		FALSE
02/11/20	Monday	1	1		TRUE
03/11/20	Tuesday	1	1		TRUE
04/11/20	Wednesday	1	1		TRUE
05/11/20	Thursday	1	1		TRUE
06/11/20	Friday	1	1		TRUE
07/11/20	Saturday	0	1		FALSE
08/11/20	Sunday	0	1		FALSE
09/11/20	Monday	1	1		TRUE
10/11/20	Tuesday	1	1		TRUE
11/11/20	Wednesday	1	1		TRUE
12/11/20	Thursday	1	1		TRUE
13/11/20	Friday	1	1		TRUE
14/11/20	Saturday	0	1		FALSE
15/11/20	Sunday	0	1		FALSE
16/11/20	Monday	1	1		TRUE
17/11/20	Tuesday	1	1		TRUE
18/11/20	Wednesday	1	1		TRUE
19/11/20	Thursday	1	1		TRUE
20/11/20	Friday	1	1		TRUE
21/11/20	Saturday	0	1		FALSE
22/11/20	Sunday	0	1		FALSE
23/11/20	Monday	1	1		TRUE
24/11/20	Tuesday	1	1		TRUE
25/11/20	Wednesday	1	1		TRUE
26/11/20	Thursday	1	1		TRUE
27/11/20	Friday	1	1		TRUE

				Total (days)	78
				Total (hours)	468

## SWModel
Task	Planned	Completed	Remaining
Search for 5 open source BLAST algorithm software implementations	30	10	20
Running best implementation with 10 genomes	30	0	30
Develop C-model compatible with C-RTL cosimulation	40		40
Documentation	5		5
Round 2			0
Improvements	10		10
			0
			0
			0
Round 3			0
Improvements	10		10
			0
			0
			0
			0
			0
			0
			0
Total	125	10	115

## RTL_Design
Task	Planned	Completed	Remaining
Architecting the design hierarchy, clocks, control registers	10	10	0
Implementation of 10 sub modules	50	0	50
			0
documentation	5		5
Round 2			0
Rearchitecting	5		5
Reimplementing	10		10
			0
			0
Optimization			0
Area minimization	10		10
Speed improvement	20		20
Code cleanup for readability and maintainability	5		5
			0
			0
			0
			0
			0
Total	115	10	105

## Verification
Task	Planned	Completed	Remaining
Develop verification plan – coverage goals	10	5	5
			0
			0
			0
Create bit accurate SV behavioral model matching C model	30	10	20
Setup UVM verification environment	30	0	30
Write UVM tests covering important features	20		20
Create directed tests for hard to hit coverage points	5		5
			0
Run regression and fix bugs from failing tests	40		40
			0
Optimize			0
Reduce test count by enhanced randomization	10		10
			0
			0
Review coverage	5		5
			0
			0
Total	150	15	135

## FPGA_prototyping
Task	Planned	Completed	Remaining
Choose target FPGA	5	5	0
Synthesize and run first version of RTL	20	0	20
Add debug logic analyzers	5		5
Synthesize and run second version of RTL	10		10
			0
Add instrumentation to FPGA for coverage collection	15		15
			0
			0
			0
			0
			0
			0
			0
			0
			0
			0
			0
			0
Total	55	5	50

## Demo
Task	Planned	Completed	Remaining
			0
Plan demo – What genomes to be compared by BLAST	5	0	5
Plan contents of the demo	5		5
			0
Invite participants – online/direct	10		10
			0
Rehearsal for demo	5		5
			0
			0
			0
			0
			0
			0
			0
			0
Actual demo	5		5
Post demo customer questions	2		2
			0
Total	32	0	32

## Signoff
Task	Planned	Completed	Remaining
			0
Checklist item 1	1		1
Checklist item 2	1		1
Checklist item 3	1		1
Checklist item 4	1		1
Checklist item 5	1		1
Checklist item 6	1		1
Checklist item 7	1		1
Checklist item 8	1		1
Checklist item 9	1		1
Checklist item 10	1		1
			0
			0
			0
			0
			0
			0
			0
Total	10	0	10